## Projections & Estimates
Projections and Estimates
| 1 | 4 | 1 | Weighting
High Level Tasks | Most Pessimistic | Most Likely | Most Optimistic | Pert Estimation |  | Tasks >= 100
High Level Design | 64 | 36 | 32 | 40 |  | 3
Technical Design | 160 | 115 | 100 | 120
Development | 760 | 575 | 480 | 590
Unit Testing | 100 | 70 | 40 | 70
Integrated Testing | 110 | 80 | 50 | 80
User Acceptance Testing | 130 | 110 | 30 | 100
TOTAL HOURS |  |  |  | 1000
Estimated Fixed Expenses | 100280 |  | Expenses
5% | 96600 |  | Previous Fixed Expenses | 92000
6.5% | 97980 |  | Estimated Increase | 9%
8% | 99360
9.5% | 100740
11% | 102120 |  | Sales
12.5% | 103500 |  | Sale Price | 35
14% | 104880 |  | Previous Sales Units | 4700
15.5% | 106260 |  | Expected Increase | 7%
Estimated Income
176015 | 30 | 32.5 | 35 | 37.5 | 40 | 42.5 | 45
3% | 145230 | 157332.5 | 169435 | 181537.5 | 193640 | 205742.5 | 217845
4% | 146640 | 158860 | 171080 | 183300 | 195520 | 207740 | 219960
5% | 148050 | 160387.5 | 172725 | 185062.5 | 197400 | 209737.5 | 222075
6% | 149460 | 161915 | 174370 | 186825 | 199280 | 211735 | 224190
8% | 152280 | 164970 | 177660 | 190350 | 203040 | 215730 | 228420
9% | 153690 | 166497.5 | 179305 | 192112.5 | 204920 | 217727.5 | 230535
10% | 155100 | 168025 | 180950 | 193875 | 206800 | 219725 | 232650
11% | 156510 | 169552.5 | 182595 | 195637.5 | 208680 | 221722.5 | 234765

## Scenario Summary
Scenario Summary
|  | Current Values: | 20 weeks | 30 weeks | 21 weeks | 42 weeks
|  |  | Created by Aastha on 8/18/2022 | Created by Aastha on 18-08-2022 | Created by Aastha on 8/18/2022 | Created by Aastha on 8/18/2022
Changing Cells:
| Total_staff | 10 | 11.4471 | 10 | 12 | 10
| Working_day__hours | 6.8 | 9.1577 | 8 | 8 | 6.8
| Working_week__days | 4.25 | 5.7236 | 5 | 6 | 4.25
Result Cells:
| Projected_Profit | 198800 | -100225.4239 | 86300 | -44950 | 198800
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.

## Scenario Summary 2
Scenario Summary
|  | Current Values: | Current Price | Price Decrease | Price Increase
|  |  | Created by Aastha on 18-08-2022 | Created by Aastha on 18-08-2022 | Created by Aastha on 18-08-2022
Changing Cells:
| Sale_Price | 35 | 35 | 30 | 40
| Quantity_Sold__Per_Manual | 2140 | 2140 | 2461 | 1819
Result Cells:
| Projected_Profit | 80000 | 80000 | 67594.2029 | 55188.4058
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.

## Project Costing Model
Project Costing Overview
Project Variables |  | Project Duration
Software Manuals | 12 | Total effort (hours) | 12000
Man Hours per Manual | 1000 | Total working week (hours) | 289.0002
Total staff | 10 | Calculated duration (weeks) | 41.5225
Working day (hours) | 6.8
Working week (days) | 4.25 | Salary calculations (per person per week)
Standard Work Week Hours | 35 | Total hours per week | 28.9
Standard Hourly Rate | 50 | Base salary ($50 per hour up to 40 hours per week) | 1445.0009
Overtime Hourly Rate | 75 | Overtime salary ($75 per hour over 40 hours per week) | 0
Costs |  | Revenues
Weekly salary (per person) | 1445.0009 | Sale Price | 35
Total weekly salaries | 14450.0093 | Quantity Sold (Per Manual) | 2140
Total project salaries | 600000 | Per Manual Revenue | 74900
Fixed Overheads | 100000 | Total Revenue | 898800
Total Project Costs | 700000 | Projected Profit | 198800